## Summary
Local Maternity & Neonatal System (LMNS) Equity & Equality Action Plan: Mid & South Essex
| Action Plan Contents |  | 1. Restore NHS services inclusively
2. Mitigate against digital exclusion
3. Ensure datasets are timely and complete
4a. Coproduced Interventions
4b. Maternal mortality, morbidity and experience
4c. Perinatal mortality and morbidity
4d. Support for maternity and neonatal staff
4e. Enablers
5. Strengthen leadership and accountability
| Document Author: | Gemma Hickford meccg.localmaternityneonatalsytem@nhs.net
| ICS Approval: | MSE LMNS Steering Board 27/09/22

## 1 Restore Services
Mid and South Essex Equity and Equality Action Plan August 2022
Action/Goal | Specific - What do we want to achieve? | By when | Action Number | Metrics for Success
Restore NHS Services Inclusively
Continue to implement the Covid-19 four actions | Audit the implementation of MSEFT operational guidance (Care of Black, Asian and minority ethnicty pregnant women during COVID-19 pandemic policy) reflecting the NHSE Four Key Actions guidance, to identify areas of ongoing focus for the LMNS. | 2022-08-31 | 1 | Implementation of the COVID-19 four actions
| Undertake a review of the operational guidance advising how the risks of COVID-19 for pregnant women from ethnic minority groups are managed to ensure it continues to meet the needs of services. | 2023-03-31 | 2 | Updated guidance available within maternity services at MSEFT.
Ensure maternity staff are equipped to provide safe and high quality maternity care, to those at-risk pregnant women/people from ethnic minority groups | Identify additional training and support for maternity staff in relation to at-risk groups, ensuring effective review, admission and MDT escalation processes are in place. | 2022-12-31 | 3 | Provider training provision data including attendance
Ensure LMNS communications are consistently tailored to reflect an inclusive approach | Recruit an LMNS Communications Officer role to provide expertise and guidance consistently in relation to information that is shared with both staff and the public. | 2022-12-31 | 4 | Successful recruitment wihtin timeline identified. Agreed evaluation approach.
| Seek to ensure all LMNS communications, where possible, are coproduced with the MNVP to ensure information reflects service users needs and uses inclusive and additive language. | 2022-08-31 | 5 | Service user feedback and evaluation
Monitor the reported uptake of folic acid, with particular focus on those from ethnic minority groups and those living in areas of greatest deprivation, to identify opportunities for improvement | The LMNS will monitor the reported uptake of folic acid, and where possible vitamin D, to evaluate the need to improve access and awareness of pre-conceptual through to postnatal supplementation. | 31/09/2023 | 6 | Women using folic acid (source: Regional Measures Report)
Ensure maternity providers record in maternity information systems, ethnicity, postcode, co-morbidities, BMI and age to identify those at greatest risk of poor outcomes | Review current EPR systems, to ensure they identify key information highlighting specified risk factors. Where this is not achieved currently, consider alternative actions to address this where possible. | 2022-12-31 | 7 | EPR systems provide access to key information indicating risk factors.
Ensure that providers offer face-to-face care to patients who cannot use remote services | Review the provision of maternity care, ensuring that clinical services are face-to-face for those with no access to remote services. | 2022-12-01 | 8 | Face-to-face care provision for all that need it.

## 2 Digital Exclusion
Action/Goal | Specific - What do we want to achieve? | By when | Action Number | Metrics for Success
Mitigate against digital exclusion
Ensure that providers offer face-to-face care to patients who cannot use remote services | Review the provision of maternity care, ensuring that clinical services are face-to-face for those with no access to remote services. | 2022-12-01 | 1 | Care delivery is face to face for all without access to remote services.
Identify potential variation between specified groups, in relation to how maternity care is accessed | Ensure that data collection is carried out, to identify who is accessing face-to-face, telephone or video consultations, including by relevant protected characteristic and health inclusion groups | 2024-03-01 | 2 | Data available identifying the format of care provision during maternity care.
Assess the impact of digital consultation channels in relation to patient access | Review whether digital consultation use has impacted service user access within maternity services | 2023-12-31 | 3 | Service user experience measure
Ensure personalised care and support plans (PCSP’s) are available in a range of languages and formats | Initiation of a Personalisation and Choice workstream within provider organisations | 2022-07-01 | 4 | Workstream in place
| Develop a standardised hard copy PCSP format for use across maternity services in the system. | 2022-12-31 | 5 | 1. Ensure that every women/person is offered a personalised care and support plan in line with guidance. 2. The number of women with a Personalised Care and Support Plan which covers: a) antenatal care by 17 weeks gestation b) intrapartum care by 35 weeks gestation c) postnatal care by 37 weeks gestation 3. The numbers of women who had all three of the above in place by the gestational dates Available via the MSDS by ethnicity and IMD
| Prioritise and support the introduction of a digital trust wide platform within maternity, to enable access to patient records, a digital PCSP, appointments, etc. | 2023-12-31 | 6 | Introduction of platform to support maternity services deliver digital access
| Ensure PCSP's are available in a range of languages | 2023-12-31 | 7 | Provision of PCSP's in various languages
| Promote the use of CardMedic across maternity services, to support improved communication with all service users/patients, and to reduce health inequalities. | 2022-05-01 | 8 | CardMedic launched and in use within maternity services

## 3 Datasets
Action/Goal | Specific - What do we want to achieve? | By when | Action Number | Metrics for Success
Ensure datasets are complete and timely
On maternity information systems continuously improve the data quality of ethnic coding and the mother’s postcode | Evaluate MSDS data to monitor the inclusion of a valid ethnicity category for women/people booked each month. Not stated, missing and not known are not valid records (CNST Safety Action 2) | 2022-12-31 | 19 | CNST Safety action 2, category 10: data submitted to MSDS includes a valid ethnic category for at least 80% of the women booked in the month. Not stated, missing and not known are not valid records Ethnicity data quality reported by the Regional Measures report.
| Evaluate MSDS data to monitor the inclusion of valid postcodes for all women at booking each month (CNST Safety Action 2) | 2022-12-31 | 20 | CNST Safety action 2, category 9: data submitted to MSDS contains valid postcode for mother at booking in 95% of women booked in the month.

## 4a Coproduced Interventions
Action/Goal | Specific - What do we want to achieve? | By when | Action No. | Metrics for Success
4a) Understand your population and co-produce interventions
Understand the local population's maternal and perinatal health needs (Include social determinants of health) | Undertake a population analysis to understand areas of focus moving forward. | 2021-11-30 | 1 | Completed
Map the community assets which help address the social determinants of health | Map the community assets | 2021-11-30 | 2 | Completed
Conduct a baseline assessment of the experience of maternity and neonatal staff by ethnicity using WRES 1 to 8 | Plan and conduct a baseline assessment for Maternity and Neonatal staff WRES indicators 1-8 | 2021-11-30 | 3 | Completed
Set out a plan to co-produce interventions to improve equity for mothers, babies and race equality for staff | Develop a co-production plan to include improved engagement of marginalised groups | 2022-11-30 | 4 | Updated Co-production plan
| Identify further system links to support the progress of the action plan | 2022-12-31 | 5 | Identified links within the LMNS
| Support the MNVP to engage with representatives of organisations that may help increase engagement with Ethnic Minority communities | 2023-03-31 | 6 | MNVP increased engagement with ethnic minority communities

## 4b Mortality Morbidity Experien
Action/Goal | Specific - What do we want to achieve? | By when | Action No. | Metrics for Success
4b) Action on maternal mortality, morbidity and experience
Implement maternal medicine networks (MMN) to help achieve equity | Determine which MMN pathways will best serve the needs of our population. | 2022-10-31 | 1 | Formalisation of a pathway within MSEFT that meets the needs of the population who need it.
Offer referral to the NHS Diabetes Prevention Programme to women with a past diagnosis of gestational diabetes mellitus (GDM) who are not currently pregnant and do not currently have diabetes | Undertake a review of CGM uptake within MSEFT during 2021/22 | 2022-08-31 | 2 | Completion of CGM assurance audit, every quarter. Local data reporting identifying trends and themes.
| Engage and support the MSE Diabetes Prevention Programme Project Lead in their role to improve prevention and early detection of Type 2 diabetes. | 2023-03-30 | 3 | Incidence of diabetes during pregnancy within MSEFT (Type 1 and GDM).
Implement NICE CG110 antenatal care for pregnant women with complex social factors | Identify timeline required for providers to review current antenatal care pathway and address any gaps in implementation against NICE CG110. | 2023-03-31 | 4 | 1. Proportion of women with complex social factors who attend booking by 10 weeks, 12+6 weeks and 20 weeks (source: Regional Measures Report) 2. For each complex social factor grouping, the number of women who: attend for booking by 10, 12+6 and 20 weeks; and attend the recommended number of antenatal appointments
| Support the evaluation of women's experiences of antenatal care and ensure they guide future service development. | 2024-03-31 | 5 | 1. Service user evaluation analysed 2. Evidence of service development as a result of point 1.
Implement maternal mental health services with a focus on access by ethnicity and deprivation | Ensure MSEFT maternity services and MNVP involvement and engagement within the development of MMHS across Mid and South Essex | 2022-03-01 | 6 | Participation and engagement with the MMHS Task and Finish group by MSEFT and the MNVP.
| Consider access to services based on ethnicity and level of deprivation (defined by postcode) when designing MMHS. | 2023-03-31 | 7 | Monitor NHSE PMH dashboard access data by ethnicity and deprivation to understand service effectiveness.
Ensure personalised care and support plans are available to everyone | Ensure PCSP's are available to the majority of those engaging with maternity services in a format that is accessible to them. | 2024-03-31 | 8 | % of women with a PCSP at Booking,
| Undertake an audit of PCSP's which includes an experience measure at least annually | 2023-03-31 | 9 | Completion of audit (as detailed within: NHSE Personalised care and support planning guidance 2021)
Ensure the MVPs in your LMNS reflect the ethnic diversity of the local population, in line with NICE QS167 | Regularly review the membership of the MNVP, to evaluate how representative of the local population it is. | 2023-03-31 | 10 | % of parent members of the MNVP who are from ethnic minority groups (reviewed annually)
| Support the MNVP to lead a LGBTQ+ Focus Group to identify areas of focus for MSE | 2022-06-01 | 11 | Focus Group establishment and key aims identified with timelines
| Work in collaboration with the MNVP to identify opportunities for engagement with ethnic minority communities. | 2023-12-31 | 12 | Evidence of engagement and coproduction, and secondary to increased parent members from ethnic minority groups.
Improve early pregnancy access to maternity care in MSE | Improve early access to maternity care within MSE, for those in identified ethnic minority groups. | 2023-12-31 | 13 | 1. Increase the number of women/people who are Booked at <70 days gestation (Regional Measures report) 2. % of women attending the booking appointment who are from ethnic minority groups (source: Regional Measures Report) 3. Ethnicity data quality (source: Regional Measures Report)
Seek to improve all women and people's experiences of maternity care | Review maternity surrogacy guidelines to ensure they align with national guidance and recent learning reviews. | 2022-12-31 | 14 | Updated maternity guidance developed with service user input.
Improve outcomes for those at greatest risk of health inequalities | UK-USA Maternal Health Inequalities remote monitoring project at MSEFT - UK pilot | 2022-12-30 | 15 | Project agreed and initiated.

## 4c Perinatal Mortality
Action/Goal | Specific - What do we want to achieve? | By when | Action No. | Metrics for Success
4c) Action on perinatal mortality and morbidity
Implement targeted and enhanced continuity of carer, as set out in the NHS Long Term Plan. This means that, as continuity of carer is rolled out to most women, women from Black, Asian and Mixed ethnic groups and women living in deprived areas are prioritised, with 75% of women in these groups receiving continuity of carer by 2024. It also means ensuring that additional midwifery time is available to support women from the most deprived areas. | MSEFT Continuity of Carer plans must reflect a targeted approach to future rollout, in line with the LTP. | 2022-08-31 | 1 | 1. MSEFT CoC trajectory monitoring 2. Placement on a continuity of carer pathway – Black/Asian women 3. Placement on a continuity of carer pathway – women living in the most deprived areas 4. Deliveries under 27 weeks (Regional Measures report) 5. Deliveries under 37 weeks (Regional Measures report)
| Pursue CoC rollout locally in line with implementation plans. | 2026-12-31 | 2
Implement a smoke-free pregnancy pathway for mothers and their partners | Develop an enhanced Smokefree pregnancy pathway across MSE reaching all eligible for support. | 2023-03-31 | 3 | Smoke-free pregnancies ≥94%
| Recruit a Band 3 SCSW's (Smoking Cessation Support Workers) and a Smoke Free Champion Midwife to lead the service. | 2022-12-31 | 4 | Smoke-free pregnancies ≥94%
| Ensure provision of Nicotine Replacement Therapy (NRT) as part of the smokefree pregnancy pathway. | 2023-06-30 | 5 | Smoke-free pregnancies ≥94%
| Ensure accurate data reporting in relation to the pathway, to identify areas of improvement and progression. | 2022-08-31 | 6 | 1. SATOB/SATOD data for MSEFT (full metrics detailed in evidence) 2. Low birth weight (<2,500g for term births) (Regional Measures report)
| Ensure data reporting reflects ethnicity and areas of deprivation (postcodes), to enable effective oversight of service progress. | 2023-03-31 | 7 | Data reflecting those at greatest risk
| Consider innovative approaches to address smoking cessation during pregnancy, including incentivised approaches, targeted at groups who would benefit the most. | 2023-12-31 | 8 | Reduction in SATOD rates, across MSE population
Implement an LMNS breastfeeding strategy and continuously improve breastfeeding rates for women living in the most deprived areas | Support BFI accreditation across all three maternity sites of MSEFT, to improve standards of care in relation to infant feeding. | 2026-08-31 | 9 | 1. Baby Friendly accreditation (Regional Measures report) 2. Breast milk at first feed (Regional Measures Report)
| Ensure a collaborative approach to the development of an LMNS feeding strategy, involving key stakeholders, utilising the MNVP Infant Feeding Focus Group to ensure co-production | 2023-08-31 | 10 | MSE Infant feeding Strategy

## 4d Staff Support
Action/Goal | Specific - What do we want to achieve? | By when | Action No. | Metrics for Success
4d) Support for maternity and neonatal staff (Cultural Intelligence and WRES)
Roll out multidisciplinary training about cultural competence in maternity and neonatal services | Seek to include e-LfH 3 cultural competency training modules to mandatory training programme | 2023-08-31 | 1 | % of maternity and neonatal staff who attended training about cultural competence in the last two years
When investigating serious incidents, consider the impact of culture, ethnicity and language | Ensure that ethnicity data is recorded for all Serious Incidents (SI's) and PMRT cases, with regular review undertaken to consider any themes/trends. | 2023-03-31 | 2 | 1. % of maternity and neonatal Serious Incidents relating to patient care with a valid ethnic code 2. % of Perinatal Mortality Review Tool cases with a valid ethnic code
| Ensure maternity services consider the impact of culture, ethnicity and language in relation to the antenatal risk assessment process, initial assessment and follow-up. | 2023-08-31 | 3 | Evidence of consideration in relation to antenatal risk assessment
| Ensure investigations consider whether the impact of culture, ethnicity and language on the woman’s needs was discussed and considered during the antenatal risk assessment process, initial assessment and follow-up. | 2023-08-31 | 4 | Evidence of discussion and consideration in investigations during the antenatal risk assessment, initial assessment and follow up.
Implement the Workforce Race Equality Standard (WRES) in maternity and neonatal services | Engage with providers EDI Team/Managers to review maternity and neonatal WRES data and understand provider next steps. | 2023-03-31 | 5 | WRES indicators 1 to 8 for midwives and nurses in maternity and neonatal services
| Ensure WRES data is used to identify areas where there may be a failure to recruit staff from ethnic minority groups. | 2023-08-31 | 6 | WRES Workforce indicator 1. Percentage of staff in each of the AfC Bands 1-9 and VSM compared with the percentage of staff in the overall workforce.
| Engage with EDI teams, to consider approaches to ensure Black and minority ethnic staff representation at leadership levels and across the workforce. | 2023-03-31 | 7 | Proportional representation of staff from ethnic minority groups, within the maternity and neonatal workforce.
| Review and consider actions to address NHS Staff Survey indicator findings (5-8) where analysis by ethnicity suggests inequality of experience. | 2023-08-31 | 8 | WRES data shows imporvement in areas identified.
| Work with providers to incorporate the East of England anti-racism strategy into services. | 2023-08-31 | 9 | Adoption and embedding of the strategy at LMNS and provider level.
Strategic leadership within maternity and neonatal services, to deliver the Equity and Equality plan. | Consider the role of an Maternity Equity and Inclusion Ambassador/Lead within maternity services. | 2023-03-31 | 10 | Strategic leadership role in place.

## Enablers
Action/Goal | Specific - What do we want to achieve? | By when | Action No. | Metrics for Success
4e) Enablers
Establish community hubs in the areas with the greatest maternal and perinatal health needs | Map the current provision of community sites utilised by midwives across MSE, to identify any gaps in provision. | 2023-03-31 | 1 | Completion of the mapping of cmmunity sites across MSE.
| Support Thurrock Local Authority in their application for Trailblazer status associated with the Family Hubs and Start for Life Programme. | 2023-09-30 | 2 | Successful application and ongoing working to ensure maternity services are embedded within family hubs as a key stakeholder.
Work with system partners and the VCSE sector to address the social determinants of health | Plan to establish effective working relationships with VCSE partners within MSE | 2023-03-31 | 3 | Evidence of effective working with VCSE partners, demonctrated by their involvement in maternity services
| Ensure the LMNS participates in the development of a Pan Essex Perinatal Peer Support offer, alongside Parents 1st. | 2023-03-31 | 4 | Ongoing participation and contribution to the development of the service, with the aim it becomes embedded within maternity services.
| Support effective working relationships between local authority partners in relation to public health teams, ensuring representation where appropriate and proactive engagement to address the social determinants of health in collaboration. | 2022-08-31 | 5 | Evidence is ongoing in the collaborative working between the LMNS and Local authority partners.

## 5 Leadership Accountability
Action/Goal | Specific - What do we want to achieve? | By when | Action No. | Metrics for Success
5) Strengthen leadership and accountability
To have a clear mechanism for ensuring governance and oversight of the Equity and Equality Action Plan | Defined LMNS workstream and governance structure to ensure accountability is clear for monitoring of progress | 2022-10-31 | 1 | LMNS Workstream including governance structure agreed and embedded.
| Development of an Equity and Equality dashboard to enable monitoring of specified metrics | 2022-12-31 | 2 | Dashboard developed and utilised for monitoring progress.
| Defined roles and responsibilities: including of the ICS and provider executive boardlevel leads for health inequalities, LMNS senior responsible owner, board-level safety champions, MVP(s), etc. | 2021-11-30 | 3 | Effective governance processes, leading to progress of actions and completion of the plan.
A clear mechanism for ensuring continuous clinical quality improvement exists | The LMNS Equity and Equality workstream needs to support and encourage opportunities for QI across maternity services. There should be evidence of this identified within it's Implmentation Plan, with regular reporting identifying progress. | 2023-10-30 | 4 | Mechanism in place and identified to be effective, resulting in QI projects influencing improvements in care and outcomes.